## Sheet1
Phase | Step | Percent Complete | Start Date | End Date
1. Requirements Identification and Analysis | 4.1.1: Instantitate the Framework | 25% | 2016-10-15 | 2017-02-15
1. Requirements Identification and Analysis | 4.1.2: Develop and Conduct Role-based Training | 50% | 2016-10-20 | 2017-02-20
1. Requirements Identification and Analysis | Issuance Process |  | 2016-10-15 | 2016-10-15
1. Requirements Identification and Analysis | Draft CONOPs |  | 2016-11-05
2. Portfolio Selection and Resourcing | 4.2.4: Develop Exhibits | 75% | 2016-10-20 | 2016-12-15
2. Portfolio Selection and Resourcing | 4.2.4: Develop Exhibits | 33.33% | 2016-12-20 | 2017-02-15
2. Portfolio Selection and Resourcing | 4.2.4: Develop Exhibits | 45% | 2017-03-20 | 2017-06-15
2. Portfolio Selection and Resourcing | Begin FYXX BE |  | 2016-10-20 | 2016-10-20
2. Portfolio Selection and Resourcing | CIO Advisor Declared |  | 2016-11-30
3. Test | 4.3.1 Test | 99% | 2017-01-01 | 2017-03-01
4. Performance Assessment | Qtly Report |  | 2016-11-15
4. Performance Assessment | Qtly Report |  | 2016-11-30
4. Performance Assessment | Track Metrics |  | 2017-01-01